## Tracker
ID | Wing | Ward | Description of works | Priority level | Managed by (CWM / AMU / BOV) | Partner for works | Estimated cost (<$25k, <$50k, <$100k, >$100k) | Scope of Works | Quotes | Name of contact officer on ward | Phone number | Status | Comments

## FHP Tracker (hidden)
CWM Hospital Minor Works
ID | Wing | Ward | Description of works | Priority level | Estimated cost | Status | Partner for works | Scope of Services prepared? | AMU clearance? | Quotes collected? | Name of contact officer on ward | Phone number | Comments
4 | East Wing | Physiotherapy | Construction of Waiting Area | High |  |  | FHP
8 | East Wing | ED | Extension of ED Waiting Area & Washroom | High |  |  | FHP
9 | East Wing | ED | Upgrade of the COVID Triaging Area | High |  |  | FHP
12 | East Wing | IPC | Upgrade of IPC Office | High |  | Completed | FHP
18 | East Wing | OT | Staff Tea Room & Doctors Office Upgrade | High |  |  | FHP
25 | East Wing | ASW & AMW | Storage for Both Wards | High |  |  | FHP
26 | East Wing | ASW & AMW | Bedside Lockers, Meal Tables and Benches | High |  |  | FHP
72 | West Wing | West Wing | West Wing to Children's Ward - Steel Ramp | High |  |  | FHP
79 | West Wing | Paeds | Walkway connecting West Wing Entrance to Oxfam Clinic | High |  |  | FHP
90 | West Wing | Paeds | Upgrade of Admin Area | High |  |  | FHP
91 | West Wing | Paeds | Children's Ward Washroom | High |  |  | FHP
92 | West Wing | Paeds | Mickey Mouse Room | High |  |  | FHP
93 | West Wing | Paeds | Staff Washroom | High |  |  | FHP
95 | West Wing | Bio Medical | Bio Medical Storage Area | High |  |  | FHP
5 | East Wing | Pharmacy | Upgrade of Pharmacy Storage | Low |  |  | FHP
58 | West Wing | Kitchen | Staff Wellness area | Low |  |  | FHP
6 | East Wing | Physiotherapy/Pharmacy | Extension of Walkway Shed | Medium |  |  | FHP
59 | West Wing | Kitchen | NICU Mothers Room | Medium |  |  | FHP
99 | East Wing | East Wing | Disability Access Restrooms | High |  |  | FHP
100 | East Wing | East Wing | Separate rooms for males and females (staff and patients) | High |  |  | FHP
101 | West Wing | West Wing | Separate rooms for males and females (staff and patients) | High |  |  | FHP
102 | Maternity | Maternity | Consultation room – privacy (victims of violence)- child friendly | High |  |  | FHP
103 | Maternity | Maternity | Major renovations to the Ground floor of the Maternity unit – plumbing, air conditioning, partitioning, painting, etc. joinery, accessible private counters, corridor railing | High |  |  | FHP
104 | All Units | All Units | Accessible hospital signage | High |  |  | FHP
105 | Old West Wing | Old West Wing | Emergency OT – to be set up the Old (West) Wing | High |  |  | FHP
106 | Maternity | Maternity | Showers (Install proper showerheads, shower handles and ensure hot water and cold water taps are working – plumbing) | High |  |  | FHP
45 | Maternity | Maternity | Painting of ANC - Interior and upgrading of Sewer Line | Medium |  |  | FHP? | [5 empty] | Consider improving aesthetics as part of re-painting
46 | Maternity | Maternity | Upgrade of the Scan Room - facility funded | High |  |  | FHP?
47 | Maternity | Maternity | Painting of Whole of Maternity - Interior | Medium |  |  | FHP? | [5 empty] | Consider improving aesthetics as part of re-painting
49 | Maternity | Maternity | Upgrading of CSSD Room and Foyer | Medium |  |  | FHP? | [5 empty] | For adding - upgrading of maternity staff R&R room
1 | East Wing | Extension Quarters | Vacation of Staff CWMH | Low
2 | East Wing | Extension Street | Road Improvement Upgrade Works | Low
3 | East Wing | CWM | CWM Industrial Site - Gas for Boiler, Water Tanks & Storage Containers | High
7 | East Wing | ED | East Wing Generator ATS | High
10 | East Wing | Radiology | New CT Scan Extension | Low
11 | East Wing | Medical Bay | Medical Intern Workstation | High
13 | East Wing | SOPD | Public Male and Female Washroom Upgrade | High
14 | East Wing | CWM | Walkway and Shed to Internal Medicine Office | High
15 | East Wing | CWM | Follow-up on the Liquid Oxygen Area | High
16 | East Wing | Laboratory | Anatomy Laboratory Relocation with Doctors | High
17 | East Wing | Auditorium | Upgrade of the Auditorium | Medium
19 | East Wing | OT | OT 6 & 8 Light Upgrade | High
20 | East Wing | OT | Termination of Alarm - Outside Manifold | High
21 | East Wing | CSSD | Re-look at Sterilizer, Autoclave, AC and Improvement of the Workstation | High
22 | East Wing | OT | Storage Space for OT | Medium
23 | East Wing | OT | IT govnet connection to TM | High
24 | East Wing | ASW & AMW | Public and Staff Washroom | High
27 | East Wing | East Wing | Cleaning of East Wing frontage - extension street | High
28 | East Wing | East Wing | Painting of East Wing frontage | High
29 | East Wing | East Wing | Planters on the East Wing frontage for beautification | High
30 | East Wing | east wing boiler | upgrading of steam pipes | High
31 | East Wing | east wing boiler | upgrading of steam manifold and steam line inside boiler room | High
32 | Maternity | Maternity | Painting of the exterior walls - CIU Project | High
33 | Maternity | Maternity | Upgrading of Guttering and Eave batterns | High
34 | Maternity | Maternity | Upgrading of Roof Exhaust Fan | High
35 | Maternity | Maternity | Upgrading of the Windows | High
36 | Maternity | Maternity | Sub-board Upgrade | High
37 | Maternity | Maternity | Electrical Works in Room 5 for AC - Facility Funded | High
38 | Maternity | Maternity | Boarding and Removal of the Old AC Units | High
39 | Maternity | Maternity | Securing of the Container Walkway | High
40 | Maternity | Maternity | Backup Generator Upgrade | Low
41 | Maternity | Maternity | Hook up Hyperbaric to the West Wing Backup Generator | High
42 | Maternity | Maternity | Power Assessment of Maternity and Paeds | High
43 | Maternity | Maternity | EFL Transformer and Cable Upgrading | Low
44 | Maternity | Maternity | Backup Water Supply including Pump | High
48 | Maternity | Maternity | Autoclave in Maternity CSSD | High
50 | Maternity | Maternity | West Wing OT | Low
51 | Maternity | Maternity | Blocking of Ceiling Pigeon Access | High
52 | West Wing | Kitchen | Upgrading of Top Kitchen - Cooking Area | High
53 | West Wing | Kitchen | Upgrading of Top Kitchen Roof | High
54 | West Wing | Kitchen | Upgrading of Meat Cutting Area | High
55 | West Wing | Kitchen | Painting of Top Kitchen | High
56 | West Wing | Kitchen | Upgrading of Frontage | High
57 | West Wing | Kitchen | Back up Water Tank and Pump for Kitchen | High
60 | West Wing | Kitchen | Removal of Old Steam pipes | High
61 | West Wing | Kitchen | Top Kitchen Network tower | Low
62 | West Wing | Lau Ward | Painting of Interior and Exterior | High
63 | West Wing | Lau Ward | Upgrading of Rooms, Washrooms, Sluice | High
64 | West Wing | Rewa Ward | Upgrading of Rooms, Washrooms, Sluice | Low
65 | West Wing | Rewa Ward | Painting of Interior and Exterior | Low
66 | West Wing | ANZ Ward | Painting of Interior and Exterior | Low
67 | West Wing | ANZ Ward | Upgrading of Rooms, Washrooms, Sluice | Low
68 | West Wing | WMW | Roof of the Connection between WMW and Physio | High
69 | West Wing | WMW | Upgrading of Rooms, Washrooms, Sluice | Low
70 | West Wing | WMW | Painting of Interior and Exterior | Low
71 | West Wing | Operator | Access to the Tea Room | Low
73 | West Wing | West Wing | West Wing Main Entrance Roof - Both End | High
74 | West Wing | Children's Ward | Main Entrance Roof | High
75 | West Wing | Pharmacy | Upgrade works in Inpatient Pharmacy | Medium
76 | West Wing | West Wing Lift | Upgrading of West Wing Lift | High
77 | West Wing | Laundry | All planned works - Walkway, Linen handling Area, Staff and Storage Area, Clearing of Old Boiler Room, Fitters Room, Stores | High
78 | West Wing | Laundry | Boarding of Washing Machine and Iron Rollers | High
80 | West Wing | West Wing Boiler | Old Boiler Room Maintenance Works | High
81 | West Wing | Transport | Transport Section Upgrade - New Design | Low
82 | West Wing | Hospital Services | Hospital Services Workshop, Washroom and Toilet | Low
83 | West Wing | Dental | Patient Waiting Area | High
84 | West Wing | Old Anderson Building | Dismantling of Old Anderson building | Low
85 | West Wing | Urology Clinic and IPC | Renovation and Upgrade Works | High
86 | West Wing | Quarters 51 | Upgrading, fencing and driveway | High
87 | West Wing | West Wing | Assessment of trees | Medium
88 | West Wing | West Wing | West Wing Backup tanks | High
89 | West Wing | West Wing | Assessment of Crop building | Low
94 | West Wing | Paeds | Paeds Lift | High
96 | West Wing | Paeds | Assessment of Structural as a clinical surge capacity for an outbreak | Low
97 | West Wing | Paeds | Blocking of Ceiling Pigeon Access | High
98 | West Wing | West Wing | Removal of Old Boiler Chimney | High

## Definitions
Priority | Status | Category | Cost
Urgent | Scoping | Yes | <$10,000
High | Approvals in process | No | $10,000-$50,000
Moderate | Works underway |  | $50,000+
Low | Completed
Delayed